## Sheet1
Duration | PV | AC | EV | Project Status
0 | 0 | 0 | 0 | Project is over-budget by 1500 hrs
7.5 | 5000 | 7000 | 5500 | Project is not delayed, it is ahead by 500 hrs, which is equivalent to 10 days (5 Engineers, 10 Working Hrs/Day)
15 | 10000