## Estimation
| Hours | Cost
Testing servers | 1000 | 10000
Testing UPS | 2000 | 20000
Integration with Google Maps | 500 | 5000
Dealing with several restaurants about discount | 500 | 5000
Working on user guidance for clients | 4000 | 40000
Developing software | 10000 | 100000
| 18000 | 180000
Tools/Suppliers Cost | - | 360000
Total Cost | - | 540000

## ToolsSuppliers
Cost
Servers | 100000
UPS | 100000
Google Supplier | 10000
Discount Suppliers | 150000
360000

## Assumptions
Assumptions
1 | Using QuestMap supplier instead of Google Maps may take longer hours to deal with them
2 | Some discounts are seasonal, so some restaurants cannot afford discounts
3 | User guidance is not clear enough for clients, so it may need several updates to improve it